## Answer Report 1
Microsoft Excel 11.0 Answer Report
Worksheet: [DotCom_Project.xls]model
Report Created: 3/31/2005 10:49:41 AM
Result: Solver found a solution. All constraints and optimality conditions are satisfied.
Engine: Standard LP/Quadratic
Target Cell (Min)
| Cell | Name | Original Value | Final Value
| $D$23 | Project_Duration | 38 | 38
Adjustable Cells
| Cell | Name | Original Value | Final Value
| $G$6 | A Start Day | 2 | 2
| $G$7 | B Start Day | 0 | 0
| $G$8 | C Start Day | 18 | 18
| $G$9 | D Start Day | 22 | 22
| $G$10 | E Start Day | 12 | 12
| $G$11 | F Start Day | 19 | 19
| $G$12 | G Start Day | 22 | 22
| $G$13 | H Start Day | 20 | 20
| $G$14 | I Start Day | 19 | 19
| $G$15 | J Start Day | 26 | 26
| $G$16 | K Start Day | 23 | 23
| $G$17 | L Start Day | 30 | 30
| $G$18 | M Start Day | 29 | 29
| $G$19 | N Start Day | 31 | 31
| $D$23 | Project_Duration | 38 | 38
Constraints
| Cell | Name | Cell Value | Formula | Status | Slack
| $I$6 | A End Day | 12 | $I$6<=$D$23 | Not Binding | 26
| $I$7 | B End Day | 19 | $I$7<=$D$23 | Not Binding | 19
| $I$8 | C End Day | 31 | $I$8<=$D$23 | Not Binding | 7
| $I$9 | D End Day | 30 | $I$9<=$D$23 | Not Binding | 8
| $I$10 | E End Day | 26 | $I$10<=$D$23 | Not Binding | 12
| $I$11 | F End Day | 23 | $I$11<=$D$23 | Not Binding | 15
| $I$12 | G End Day | 23 | $I$12<=$D$23 | Not Binding | 15
| $I$13 | H End Day | 23 | $I$13<=$D$23 | Not Binding | 15
| $I$14 | I End Day | 24 | $I$14<=$D$23 | Not Binding | 14
| $I$15 | J End Day | 30 | $I$15<=$D$23 | Not Binding | 8
| $I$16 | K End Day | 29 | $I$16<=$D$23 | Not Binding | 9
| $I$17 | L End Day | 38 | $I$17<=$D$23 | Binding | 0
| $I$18 | M End Day | 38 | $I$18<=$D$23 | Binding | 0
| $I$19 | N End Day | 38 | $I$19<=$D$23 | Binding | 0
| $J$9 | D >= Pred #1 | 12 | $J$9<=$G$9 | Not Binding | 10
| $J$10 | E >= Pred #1 | 12 | $J$10<=$G$10 | Binding | 0
| $J$11 | F >= Pred #1 | 19 | $J$11<=$G$11 | Binding | 0
| $J$12 | G >= Pred #1 | 19 | $J$12<=$G$12 | Not Binding | 3
| $J$13 | H >= Pred #1 | 19 | $J$13<=$G$13 | Not Binding | 1
| $J$14 | I >= Pred #1 | 19 | $J$14<=$G$14 | Binding | 0
| $J$15 | J >= Pred #1 | 26 | $J$15<=$G$15 | Binding | 0
| $J$16 | K >= Pred #1 | 23 | $J$16<=$G$16 | Binding | 0
| $J$17 | L >= Pred #1 | 30 | $J$17<=$G$17 | Binding | 0
| $J$18 | M >= Pred #1 | 29 | $J$18<=$G$18 | Binding | 0
| $J$19 | N >= Pred #1 | 31 | $J$19<=$G$19 | Binding | 0
| $K$15 | J >= Pred #2 | 23 | $K$15<=$G$15 | Not Binding | 3
| $K$16 | K >= Pred #2 | 23 | $K$16<=$G$16 | Binding | 0
| $K$17 | L >= Pred #2 | 30 | $K$17<=$G$17 | Binding | 0
| $K$18 | M >= Pred #2 | 0 | $K$18<=$G$18 | Not Binding | 29
| $K$19 | N >= Pred #2 | 24 | $K$19<=$G$19 | Not Binding | 7
| $L$15 | J >= Pred #3 | 23 | $L$15<=$G$15 | Not Binding | 3
| $L$16 | K >= Pred #3 | 23 | $L$16<=$G$16 | Binding | 0

## Sensitivity Report 1
Microsoft Excel 11.0 Sensitivity Report
Worksheet: [DotCom_Project.xls]model
Report Created: 3/31/2005 10:49:42 AM
Adjustable Cells
|  |  | Final | Reduced | Objective | Allowable | Allowable
| Cell | Name | Value | Cost | Coefficient | Increase | Decrease
| $G$6 | A Start Day | 2 | 0 | 0 | 0 | 1
| $G$7 | B Start Day | 0 | 1 | 0 | 1e+30 | 1
| $G$8 | C Start Day | 18 | 0 | 0 | 0 | 1
| $G$9 | D Start Day | 22 | 0 | 0 | 0 | 1
| $G$10 | E Start Day | 12 | 0 | 0 | 0 | 1
| $G$11 | F Start Day | 19 | 0 | 0 | 1e+30 | 1
| $G$12 | G Start Day | 22 | 0 | 0 | 0 | 1
| $G$13 | H Start Day | 20 | 0 | 0 | 0 | 1
| $G$14 | I Start Day | 19 | 0 | 0 | 1e+30 | 0
| $G$15 | J Start Day | 26 | 0 | 0 | 0 | 1
| $G$16 | K Start Day | 23 | 0 | 0 | 1e+30 | 1
| $G$17 | L Start Day | 30 | 0 | 0 | 0 | 1
| $G$18 | M Start Day | 29 | 0 | 0 | 1e+30 | 1
| $G$19 | N Start Day | 31 | 0 | 0 | 0 | 1
| $D$23 | Project_Duration | 38 | 0 | 1 | 1e+30 | 1
Constraints
|  |  | Final | Shadow | Constraint | Allowable | Allowable
| Cell | Name | Value | Price | R.H. Side | Increase | Decrease
| $I$6 | A End Day | 12 | 0 | 0 | 1e+30 | 26
| $I$7 | B End Day | 19 | 0 | 0 | 1e+30 | 19
| $I$8 | C End Day | 31 | 0 | 0 | 1e+30 | 7
| $I$9 | D End Day | 30 | 0 | 0 | 1e+30 | 8
| $I$10 | E End Day | 26 | 0 | 0 | 1e+30 | 12
| $I$11 | F End Day | 23 | 0 | 0 | 1e+30 | 15
| $I$12 | G End Day | 23 | 0 | 0 | 1e+30 | 15
| $I$13 | H End Day | 23 | 0 | 0 | 1e+30 | 15
| $I$14 | I End Day | 24 | 0 | 0 | 1e+30 | 14
| $I$15 | J End Day | 30 | 0 | 0 | 1e+30 | 8
| $I$16 | K End Day | 29 | 0 | 0 | 1e+30 | 9
| $I$17 | L End Day | 38 | 0 | 0 | 8 | 2
| $I$18 | M End Day | 38 | -1 | 0 | 2 | 1e+30
| $I$19 | N End Day | 38 | 0 | 0 | 7 | 7
| $J$9 | D >= Pred #1 | 12 | 0 | 0 | 1e+30 | 10
| $J$10 | E >= Pred #1 | 12 | 0 | 0 | 10 | 2
| $J$11 | F >= Pred #1 | 19 | -1 | 0 | 1 | 1e+30
| $J$12 | G >= Pred #1 | 19 | 0 | 0 | 1e+30 | 3
| $J$13 | H >= Pred #1 | 19 | 0 | 0 | 1e+30 | 1
| $J$14 | I >= Pred #1 | 19 | 0 | 0 | 19 | 7
| $J$15 | J >= Pred #1 | 26 | 0 | 0 | 10 | 2
| $J$16 | K >= Pred #1 | 23 | -1 | 0 | 1 | 1e+30
| $J$17 | L >= Pred #1 | 30 | 0 | 0 | 8 | 10
| $J$18 | M >= Pred #1 | 29 | -1 | 0 | 2 | 1e+30
| $J$19 | N >= Pred #1 | 31 | 0 | 0 | 7 | 18
| $K$15 | J >= Pred #2 | 23 | 0 | 0 | 1e+30 | 3
| $K$16 | K >= Pred #2 | 23 | 0 | 0 | 3 | 3
| $K$17 | L >= Pred #2 | 30 | 0 | 0 | 8 | 2
| $K$18 | M >= Pred #2 | 0 | 0 | 0 | 1e+30 | 29
| $K$19 | N >= Pred #2 | 24 | 0 | 0 | 1e+30 | 7
| $L$15 | J >= Pred #3 | 23 | 0 | 0 | 1e+30 | 3
| $L$16 | K >= Pred #3 | 23 | 0 | 0 | 15 | 1

## model
LP Project Planning Example: DotCom
|  |  | Possible |  |  | # days to |  | End Days of Predecessors
| Jobs | Duration | days red. | $ per day | Start Day | speed up | End Day | >= Pred #1 | >= Pred #2 | >= Pred #3
| A | 10 | 5 | 500 | 2 | 0 | 12
| B | 19 | 4 | 600 | 0 | 0 | 19
| C | 13 | 6 | 100 | 18 | 0 | 31
| D | 8 | 0 |  | 22 | 0 | 30 | 12
| E | 14 | 2 | 200 | 12 | 0 | 26 | 12
| F | 4 | 2 | 200 | 19 | 0 | 23 | 19
| G | 1 | 0 |  | 22 | 0 | 23 | 19
| H | 3 | 1 | 300 | 20 | 0 | 23 | 19
| I | 5 | 0 |  | 19 | 0 | 24 | 19
| J | 4 | 4 | 300 | 26 | 0 | 30 | 26 | 23 | 23
| K | 6 | 0 |  | 23 | 0 | 29 | 23 | 23 | 23
| L | 8 | 0 |  | 30 | 0 | 38 | 30 | 30
| M | 9 | 3 | 400 | 29 | 0 | 38 | 29 | 0
| N | 7 | 0 |  | 31 | 0 | 38 | 31 | 24
0
| Project Duration |  | 38
Time Constraint
| Speed-up cost |  | 0

## chart
Time |  |  | Marginal
Constraint | Speedup | Cost | Cost
38 | 0 | 0
37 | 1 | 200 | 200
36 | 2 | 600 | 400
35 | 3 | 1200 | 600
34 | 4 | 1800 | 600
33 | 5 | 2600 | 800
32 | 6 | 3500 | 900
31 | 7 | 4400 | 900
30 | 8 | 5300 | 900
29 | 9 | 6400 | 1100