## Slide 1: Project Management
Patrick Johanns, BS, MBA, PhD
Phone: (319) 335-0949
Patrick-Johanns@uiowa.edu

## Slide 2: Introductions
Who am I?
Patrick Johanns, BS, MBA, PhD
Started as scientific researcher
Managed projects
Organizational improvement

## Slide 3: Class Roadmap
Preliminary Concept/Charter
  Define Project
  Project Vision and Scope Statement
  Finalize Charter
Schedule
Implement Project Plan
Monitor and Control the Plan
Close Out Project

## Slide 4: Why Project Management?
PM is used to plan, organize and accomplish non-routine work … or work in a project-based organization.
Individuals and teams are assigned responsibility and accountability for achieving organizational goals.

## Slide 5: “Seat-of-the-Pants”
“Based on or using intuition and experience rather than a plan or method; improvised”
http://www.thefreedictionary.com/

## Slide 6: Stress …
Chart: Time
Formal PM | 0 | 3.5 | 1.5 | 1 | 0.5
Seat of the Pants | 0 | 0.5 | 1 | 3 | 10

## Slide 7: Project Success …
Chart: Project Success
| Successful | Missed Targets | Failed (cancelled)
Column2 | 32 | 44 | 24
Column1

## Slide 8: A PM Methodology
Every organization should develop a project management methodology.
Otherwise:
  Everyone will manage projects intuitively.
  Targets will rarely be met
  Clients and Stakeholders will be unhappy!!

## Slide 9: A Predictable System
Reduces Risk
Provides order and overall predictability
Produces consistent results
Provides a roadmap & better control
Increases success in meeting objectives
Reduces stress on the project team

## Slide 10: A Predictable System
Allows average people to do above-average work
Is constantly improved by “lessons learned” exercises (compound interest)
Documented in manual-form -- there is no question as to how the work is done!

## Slide 11: Why Project Management?
PM is used to plan, organize and accomplish non-routine work … or work in a project-based organization.
Individuals and teams are assigned responsibility and accountability for achieving organizational goals.

## Slide 12: What is Project Management?
Project management is the informed use of specific tools and techniques to meet defined project requirements.

## Slide 13: The Project Life Cycle
Initiate the Project
Develop Project Management Plan
Implement Project Management Plan
Monitor and Control the Project
Close Out Project

## Slide 14: Definition of a Project
  A project creates a “one-time” outcome within a specified timeframe.
  A project is a temporary endeavor undertaken to produce a unique product, service, or result. (PMBOK Guide)

## Slide 15: Objectives or Constraints
Every project has four project objectives or constraints.
They are scope, time, cost, and performance.
They are interdependent.

## Slide 16: Scope
A detailed description of the project and its product outlining the magnitude of what we are working to accomplish.
The work that needs to be done to deliver the desired result … and only that work!

## Slide 17: Time
When does it have to be completed?
When will it be done?

## Slide 18: Cost
What is the total cost?
What is our budget?

## Slide 19: Performance
How good does it have to be?
Quality level.
Ford, Lexus or Yugo?

## Slide 20: Project Team
"A team is a small number of people with complementary skills who are committed to a common purpose, performance goals, and approach for which they hold themselves mutually accountable."
(Katzenbach & Smith 1994, page 45)

## Slide 21: Project Team
Projects are accomplished through teamwork.
Teamwork is synonymous with meetings.
Meetings are a principal tool for managing projects!

## Slide 22: Project Team
Project managers have to manage meetings!
… or meetings will manage them!!

## Slide 23: Project Team Meetings
Operational Foundation:
  Mining Group Gold by Thomas Kayser (2011)

## Slide 24: Project Team Meetings
  PDORA
  Purpose
  Desired Outcomes
  Roles
  Agenda

## Slide 25: Project Team Meetings
Key roles for meeting management:
In Mining Group Gold, Kayser (2011) discusses assigning roles to team members to maximize meeting efficiency. Roles:
  Primary Facilitator
  Secondary Facilitators
  Time Keeper
  Minute Taker
  Scribe

## Slide 26: Project Team Meetings
Primary Facilitator – usually the project manager.
The primary facilitator keeps the meeting on track by providing structure and focus.
Keeps a eye on meeting progress and takes appropriate action to keep meeting productive.
Responsible for keeping everyone active and involved.
Input from all members is essential for success.

## Slide 27: Project Team Meetings
Timekeeper monitors the clock and advises the team of the meeting’s progress.
Updates the team with periodic warnings as to where they are with respect to assigned times.

## Slide 28: Project Team Meetings
The Minute Taker records key decisions, action items and assignments.
Minute Takers do not write a play-by-play account of all discussions.
Meeting minutes are recorded on standard forms and distributed according to the communication plan.

## Slide 29: Project Team Meetings
The Scribe tracks discussion by writing on a flip chart and taping completed flipchart pages to the wall.
Displaying flipchart pages helps team members see how ideas and decisions develop.
Writes the agenda on a flipchart page at the beginning of the meeting for team members to follow.
Scribes collect ideas for a “parking lot” as needed.

## Slide 30: The Launch Meeting
Every project has one!!!
Make certain that you have a good one!!
Instill value!!

## Slide 31: The Launch Meeting
Committing to the project:
team members agree to specific commitments
might include:
  accepting responsibility for individual actions;
  committing to seeing the project through;
  working within professional capabilities;
  being part of the “building crew”.

## Slide 32: The Launch Meeting
Developing team ground rules:
apply to team member behavior during meetings.
helps members be more productive and at ease.
could include:
keeping an open mind to people's input; encourage equal participation;
keeping discussions confidential;
helping everyone be successful;
established by the team and agreed to by the team.
enforced by the team.

## Slide 33: The Launch Meeting
Determining meeting guidelines:
nail down meeting times and locations.
define standards such as agenda format and other templates

## Slide 34: The Launch Meeting
Create a parking lot
during the course of meetings ideas come forth that may not be germane to the agenda.
save these ideas for future discussion.
collect them in a "parking lot".
can be a separate flipchart page with a running list of issues or jot down issues on Post-It notes.
simply a method for collecting ideas.

## Slide 35: The Launch Meeting
Create an issues list or action log:
numbered register of issues being tracked.
includes issue description and who wants it resolved; target and actual resolution date.
includes description of how issue resolved.
reviewed at each meeting to manage status.

## Slide 36: The Launch Meeting
Team Charter:
Establishes the team and records its rules of engagement (commitment agreement, ground rules, guidelines, etc.).

## Slide 37: Project Launch Meeting
Activity

## Slide 38: The Project Charter
Defining the Problem
Articulating the Vision
Developing the Charter

## Slide 39: The Project Life Cycle
Initiate the Project
Develop Project Management Plan
Implement Project Management Plan
Monitor and Control the Project
Close Out Project

## Slide 40: The Project Life Cycle
Project Management answers these questions:
What problem is being addressed?
What must you do?
How will you do it?
How will you know you did it?
How well did you do?

## Slide 41: Initiation or Start-Up
High level planning yields a concept statement
Refine the project description and vision
Develop mission or scope statement
Finalize charter

## Slide 42: Define the Problem
What needs fixing?
What problem are we trying to solve?
What business situation needs to be addressed?

## Slide 43: Articulate the Vision
A vision statement helps define the project
A shared vision unites the project team.
A vision statement outlines what we are trying to accomplish.
It helps us to understand it the same way?
A well-articulated vision illuminates the completed project long before project completion.

## Slide 44: Vision/Detailed Requirements
What will it look like when the problem is solved?
What does your project create?
What does “done” look like?

## Slide 45: Vision/Detailed Requirements
Make three lists:
What are the essential “must-haves”?
Are there secondarily important “wants”?
Are there wishful thinking items that would be “nice-to-have”?

## Slide 46: Vision/Detailed Requirements
Detailed Requirements:
Include all essential “must-have” items.
As many secondary “wants” as possible.
Wishful thinking “nice-to-haves” are just that. These are your future scope creep items. Don’t include them.

## Slide 47: State the Scope (or Mission)
The scope is to accomplish the requirements on behalf of our client or major stakeholder.
This is the scope or mission statement.

## Slide 48: Project Charter
Authorizes and formally initiates the project.
Documents project purpose and requirements.
Created by the project sponsor.
If sponsor fails to do it, Charter is created by project manager/project team and approved by sponsor.

## Slide 49: Problem Statement Exercise